## Remediation Backlog
ID | Area | Title | Priority | Effort (eng-days) | Phase | Depends On | Owner | Acceptance Criteria | Evidence in Code / Review
SEC-1 | Security | Remove hardcoded JWT fallback secret + dedupe auth middleware | P0 | 2 | P0 Hardening | - | Backend Eng | Only one auth middleware exists; JWT secret comes solely from env (no literal fallback); app refuses to boot without JWT_SECRET. | backend/src/shared/middleware/auth.middleware.ts hardcodes 'svakarma_super_secret_key_2026_dev_prod'; duplicate of middleware/auth.ts
SEC-2 | Security | Add rate limiting on auth + public endpoints | P0 | 1 | P0 Hardening | - | Backend Eng | express-rate-limit applied to /auth/send-otp (e.g. 5/hr/phone), /auth/verify-otp, and global API limiter; verified via load test. | No rate limiting anywhere; send-otp brute-force / SMS-bomb possible
SEC-3 | Security | Build Zod request-validation middleware + apply to all write endpoints | P0 | 3 | P0 Hardening | - | Backend Eng | validateRequest(schema) middleware exists; auth, loans, profile, documents bodies validated; invalid payloads return 400 with field errors. | zod installed but used only in config/env.ts; controllers read req.body unchecked
SEC-4 | Security | Never return/log OTP to client; remove console OTP in prod | P0 | 1 | P0 Hardening | INT-1 | Backend Eng | OTP value never in API response or prod logs; '123456' demo shortcut gated behind NODE_ENV!=production. | auth.service.ts prints OTP to console + hardcodes 123456 for specific phones
SEC-5 | Security | Lock down CORS + tune Helmet | P0 | 1 | P0 Hardening | - | Backend Eng | CORS restricted to known app/admin origins; Helmet CSP reviewed; no wildcard in prod. | index.ts uses cors() with no origin allowlist
SEC-6 | Security | Move mobile JWT to secure storage | P0 | 1 | P0 Hardening | - | Mobile Eng | Token stored via expo-secure-store (Keychain/Keystore), not AsyncStorage; migration on app update. | myapp/services/api.js + authService.js store token in AsyncStorage('user_token')
SEC-7 | Security | Externalize mobile API base URL + enforce HTTPS | P0 | 1 | P0 Hardening | - | Mobile Eng | Base URL from Expo env/config per environment; prod uses HTTPS; no hardcoded LAN IP. | myapp/services/api.js hardcodes http://10.47.14.221:5000
INT-1 | Integration | Real SMS/OTP provider (MSG91 / Twilio / AWS SNS) | P0 | 4 | P1 Integrations | SEC-2 | Backend Eng | OTP delivered via provider; resend cooldown + max-attempt lockout; delivery failures handled; mock removed. | auth.service.ts: 'Mocked transmission - code printed to console'
INT-2 | Integration | Real credit-bureau (CIBIL) API integration | P0 | 5 | P1 Integrations | SEC-3 | Backend Eng | Live bureau pull with consent capture, caching, error/timeout handling; stub replaced; PII handled per DPDP. | cibil.service.ts generates/saves synthetic scores (generate=true)
INT-3 | Integration | Payment gateway (Razorpay) for EMI collection | P0 | 6 | P1 Integrations | SEC-3,CODE-2 | Backend Eng | Razorpay order + webhook verified (signature); EMI debit/mandate (eNACH) flow; idempotent reconciliation; repayment schedule locked during write. | No payment integration; repayment schedule has no concurrency lock
INT-4 | Integration | Cloud document storage (S3 / GCS) with signed URLs | P1 | 3 | P1 Integrations | - | Backend Eng | Uploads stored in object storage; access via short-lived signed URLs; local /uploads removed; checksum + MIME validation retained. | Multer writes to local backend/uploads served via express.static
INT-5 | Integration | Notification service (SMS/email/push) | P1 | 3 | P1 Integrations | INT-1 | Backend Eng | Loan status + EMI reminders sent via SMS/email/push (expo-notifications); templated; opt-out respected. | expo-notifications installed in mobile but no backend notification service
INT-6 | Integration | Loan underwriting + document verification workflow | P1 | 6 | P1 Integrations | INT-2 | Backend Eng + Product | Rules-based underwriting (eligibility, limits, pricing) wired to bureau + business profile; doc-verify states tracked; manual override for ops. | loan lifecycle in schema but no underwriting/approval logic; doc verify manual
INT-7 | Integration | e-signature / loan agreement (Digio / Leegality) | P1 | 3 | P1 Integrations | BIZ-2 | Backend Eng | Borrower e-signs sanction letter/agreement; signed PDF stored; audit-logged; legally compliant. | No e-signature integration found
CODE-1 | Code Quality | Delete dead duplicate referral module | P2 | 0.5 | P2 Code Quality | - | Backend Eng | modules/referrals/ removed; single referral module remains; build + routes unaffected. | Both modules/referral/ (active) and modules/referrals/ (orphaned routes) exist
CODE-2 | Data Model | Consolidate legacy 'customers' table into User model | P1 | 4 | P2 Code Quality | - | Backend Eng | Data migrated customers->User; legacy model retired or clearly archived; no dual-write paths. | schema.prisma keeps legacy 'customers' + new 'User' (duplication/migration baggage)
CODE-3 | Data Model | Add PAN/GST uniqueness + missing status index | P2 | 1 | P2 Code Quality | CODE-2 | Backend Eng | Unique constraints on PAN & GST across users; index on loan_applications.status; migration applied. | No PAN/GST unique constraint; missing index on new-model loan status
CODE-4 | Mobile | Global auth/loan state (Zustand or Context) + persistence | P1 | 4 | P2 Code Quality | SEC-6 | Mobile Eng | Auth token + user in global store, hydrated on launch; screens read from store (no refetch-on-mount); input not lost on navigation. | Screens use local useState only; no Redux/Zustand/Context; LoginScreen phone lost on nav
CODE-5 | Backend | Structured logging + request IDs | P2 | 2 | P2 Code Quality | - | Backend Eng | pino/winston logs domain events with request correlation IDs; log levels per env; PII redaction. | Only morgan('dev') HTTP logging; console.log scattered
CODE-6 | Backend | Centralize error handling via AppError + handlePrismaError | P2 | 1 | P2 Code Quality | - | Backend Eng | Single error envelope; handlePrismaError wired into global handler; no raw stack/messages leaked in prod. | errors.ts exists but handler usage inconsistent across controllers
CODE-7 | Backend | Pagination + eager loading on list endpoints | P2 | 2 | P2 Code Quality | - | Backend Eng | Loan/admin list endpoints paginated; Prisma includes eliminate N+1; verified with query logging. | No pagination; N+1 risk on loan listings
CODE-8 | Mobile | Audit/remove unused Firebase dependency | P3 | 2 | P2 Code Quality | CODE-4 | Mobile Eng | Confirm OTP is fully backend-driven; remove firebase (~heavy bundle) if unused; bundle size reduced. | firebase 12.x in mobile deps but auth uses custom backend OTP
OPS-1 | Testing | Jest + supertest: critical-path tests (auth/loans/payments) | P1 | 5 | P3 DevOps | SEC-3,INT-3 | Backend Eng | Unit + integration tests for auth, loan apply/approve, payment webhook; ~60%+ coverage on critical paths; runs in CI. | No .test/.spec files anywhere in repo
OPS-2 | DevOps | Dockerize backend + admin (+ compose with Postgres) | P1 | 2 | P3 DevOps | - | DevOps | Dockerfiles build; docker-compose spins backend+admin+Postgres locally; documented run. | No Dockerfile / docker-compose present
OPS-3 | DevOps | GitHub Actions CI/CD (lint, typecheck, test, build, deploy) | P1 | 2 | P3 DevOps | OPS-1,OPS-2,OPS-5 | DevOps | PRs run lint+typecheck+test+build; main deploys to staging; status checks required to merge. | No .github/ or any CI config
OPS-4 | Monitoring | Error tracking (Sentry) + product analytics | P1 | 2 | P3 DevOps | - | Backend + Mobile Eng | Sentry capturing backend+mobile errors with releases; analytics (Mixpanel/PostHog) on key funnels. | No monitoring/analytics integrations
OPS-5 | Code Quality | ESLint + Prettier + Husky + tsconfig strict | P2 | 1 | P3 DevOps | - | Backend Eng | Lint/format enforced; pre-commit hook; strict TS; CI fails on violations. | No linting config; no formatting standard
OPS-6 | Mobile | Expo EAS build/OTA + image optimization + lazy tabs | P3 | 3 | P3 DevOps | - | Mobile Eng | EAS build profiles + OTA updates configured; expo-image used; bottom tabs lazy-loaded. | No EAS/OTA config; expo-image unused; tabs eager
OPS-7 | DevOps | Redis caching layer (scale prep) | P3 | 2 | P3 DevOps | CODE-7 | Backend Eng | Cache hot reads (CIBIL, profile); invalidation strategy; optional until scale. | No caching strategy / Redis
BIZ-1 | Business | Secure lending capital partner (NBFC / co-lending) | P0 | 10 | P4 Business | - | Founder / BD | Signed term sheet or co-lending agreement defining capital source + economics; lending model decided (direct/marketplace/distributor). | Review: capital source unanswered — most critical gap
BIZ-2 | Business | Legal & regulatory review (RBI DLG, NBFC, DPDP) | P0 | 10 | P4 Business | - | Founder / Legal | NBFC-lawyer opinion on licensing, RBI Digital Lending Guidelines, DPDP Act 2023 obligations; remediation list produced. | Review: RBI/NBFC/DPDP exposure flagged; consult before fundraise
BIZ-3 | Business | Define explicit revenue model + unit-economics financial model | P1 | 4 | P4 Business | BIZ-1 | Founder / Finance | Documented who pays/how much; financial model with CAC, LTV, contribution margin, breakeven by loan vintage. | Review: revenue model vague; unit economics unvalidated
BIZ-4 | Business | GTM plan + investor materials (deck, demo) | P1 | 5 | P4 Business | BIZ-3 | Founder / Growth | 6-month GTM (beta->tier-2->B2B2C); pitch deck + demo video; acquisition budget + channel plan. | Review: no documented GTM; no investor materials
BIZ-5 | Business | Beta with 50-100 real SMBs + metrics instrumentation | P1 | 8 | P4 Business | INT-1,INT-2,INT-3,OPS-4 | Product / Growth | Closed beta live; instrumented for approval rate, default rate, D7/D30 retention, NPS; data informs PMF. | Review: no traction data; beta should be real SMBs, not team
|  | TOTAL ENGINEERING EFFORT |  | 110.5

## Legend & Phases
Priority | Meaning
P0 | Blocker / security or launch-critical — do first
P1 | High — needed for a real production MVP
P2 | Medium — quality, maintainability, scale prep
P3 | Low — nice-to-have / post-PMF
Phase | Focus | Indicative window
P0 Hardening | Security fixes needing no external accounts | Week 1
P1 Integrations | OTP, CIBIL, payments, storage, underwriting | Weeks 2-5
P2 Code Quality | State, schema, logging, errors, pagination | Weeks 2-5 (parallel)
P3 DevOps | Tests, Docker, CI/CD, monitoring, lint | Weeks 3-6
P4 Business | Capital partner, legal, revenue, GTM, beta | Parallel, founder-led