SVAKARMA

# Remediation Roadmap

From mid-stage MVP to production-ready, fundable product

Prepared for: Svakarma engineering & leadership

Date: June 11, 2026

Scope: Sequenced fix plan derived from the Developer & Business Review + a direct audit of the codebase

# Contents

# How to read this roadmap

This document turns “fix everything” into an ordered plan. Every item here maps to a concrete gap we confirmed in the code, not just the review narrative. The work splits into five phases that run on two tracks in parallel: an engineering track (Phases 0–3) and a business track (Phase 4) that the founders drive at the same time.

The companion spreadsheet, Svakarma_Remediation_Backlog.xlsx, holds all 34 items as filterable tickets with acceptance criteria, dependencies, and the exact file or finding each one addresses. Use this document to understand sequence and rationale; use the spreadsheet to assign and track work.

Priority key: P0 blocker / security or launch-critical  •  P1 needed for a real production MVP  •  P2 quality & scale prep  •  P3 post-PMF nice-to-have.

## The honest bottom line

The architecture is sound and the schema is genuinely good. What blocks launch is not rewriting — it is (1) a handful of real security holes, (2) replacing mocked integrations (OTP, CIBIL, payments) with live services, and (3) the single biggest unknown, which is not technical at all: who provides the loan capital. Engineering can reach a production-ready MVP in roughly 8–12 weeks with 2–3 engineers. The business cannot launch lending — at any code quality — until the capital partner and the regulatory posture are settled. Those two run first, in parallel, starting now.

## Effort & timeline at a glance

| Phase | Window | Effort & contents |
| --- | --- | --- |
| Phase 0 — Security hardening | ~1 week | 10 eng-days — 7 P0 fixes, no external accounts |
| Phase 1 — Core integrations | Weeks 2–5 | 30 eng-days — OTP, CIBIL, payments, storage, underwriting |
| Phase 2 — Code quality & data | Weeks 2–5 | 16.5 eng-days — runs parallel to Phase 1 |
| Phase 3 — Testing & DevOps | Weeks 3–6 | 17 eng-days — tests, Docker, CI/CD, monitoring |
| Phase 4 — Business (founder-led) | From Week 1, parallel | Capital partner & legal are P0, longest lead time |

# Phase 0 — Security hardening (Week 1)

These are fixes we can ship immediately with no external accounts. They close holes that exist in the code today and they are cheap. Do them first; nothing else should go to a real user until they are done.

| ID | Fix | Pri | Days | Owner |
| --- | --- | --- | --- | --- |
| SEC-1 | Remove hardcoded JWT fallback secret; collapse the two duplicate auth middlewares into one | P0 | 2 | Backend Eng |
| SEC-2 | Add rate limiting on /auth/send-otp, verify-otp, and a global API limiter | P0 | 1 | Backend Eng |
| SEC-3 | Build a Zod request-validation middleware and apply it to every write endpoint | P0 | 3 | Backend Eng |
| SEC-4 | Stop returning/logging the OTP; gate the ‘123456’ demo shortcut behind non-prod | P0 | 1 | Backend Eng |
| SEC-5 | Restrict CORS to known origins; review Helmet/CSP | P0 | 1 | Backend Eng |
| SEC-6 | Move the mobile token from AsyncStorage to expo-secure-store | P0 | 1 | Mobile Eng |
| SEC-7 | Externalize the mobile API base URL per environment; enforce HTTPS | P0 | 1 | Mobile Eng |

### Why these, specifically

- shared/middleware/auth.middleware.ts ships a literal fallback JWT secret (“svakarma_super_secret_key_2026_dev_prod”) and duplicates middleware/auth.ts. Anyone reading the repo can forge tokens. Delete the duplicate, require JWT_SECRET from env, and fail to boot without it.

- There is no rate limiting anywhere, so /auth/send-otp can be hammered — SMS-bomb and OTP brute-force. express-rate-limit is a few lines and must land before the real SMS provider (INT-1) goes live, or it becomes a cost and abuse problem.

- zod is installed but only used in config/env.ts. Controllers read req.body unchecked. One validateRequest(schema) middleware applied across auth/loans/profile/documents removes a whole class of bugs and injection risk.

- auth.service.ts prints the OTP to the console and returns ‘123456’ for specific phone numbers. That shortcut is fine for a demo but must never run in production.

# Phase 1 — Core integrations (Weeks 2–5)

This is where the product becomes real. Each item replaces a mock or stub with a live service and needs an account/API key from the business, so kick off vendor selection in Week 1. These are the heaviest engineering items and several gate the beta.

| ID | Fix | Pri | Days | Owner |
| --- | --- | --- | --- | --- |
| INT-1 | Real SMS/OTP provider (MSG91 / Twilio / AWS SNS) with resend cooldown + lockout | P0 | 4 | Backend Eng |
| INT-2 | Real credit-bureau (CIBIL) integration with consent capture & caching | P0 | 5 | Backend Eng |
| INT-3 | Razorpay payments: orders, verified webhooks, eNACH mandate, reconciliation | P0 | 6 | Backend Eng |
| INT-4 | Cloud document storage (S3/GCS) with signed URLs; retire local /uploads | P1 | 3 | Backend Eng |
| INT-5 | Notification service (SMS/email/push) for loan status & EMI reminders | P1 | 3 | Backend Eng |
| INT-6 | Loan underwriting rules + document-verification workflow | P1 | 6 | Backend + Product |
| INT-7 | e-signature / loan agreement (Digio / Leegality) | P1 | 3 | Backend Eng |

### Notes that matter

- cibil.service.ts currently fabricates and stores synthetic scores when generate=true. Real lending decisions cannot ride on that. The live integration also has to capture borrower consent and handle PII under the DPDP Act — coordinate with BIZ-2.

- The repayment schedule has no locking mechanism, so concurrent payment writes can corrupt it. Build INT-3 with idempotent, signature-verified webhooks and a row lock on the schedule during writes.

- Documents are written to backend/uploads and served via express.static — that neither scales nor is access-controlled. Move to object storage with short-lived signed URLs (INT-4).

- INT-6 (underwriting) is where the product’s real logic lives and where Product must define eligibility, limits, and pricing. It depends on the bureau integration (INT-2) being live.

# Phase 2 — Code quality & data model (Weeks 2–5, parallel)

These run alongside Phase 1 — different files, mostly different people. They pay down the debt the review flagged and make the integration work safer.

| ID | Fix | Pri | Days | Owner |
| --- | --- | --- | --- | --- |
| CODE-1 | Delete the dead duplicate referral module (modules/referrals/) | P2 | 0.5 | Backend Eng |
| CODE-2 | Consolidate the legacy ‘customers’ table into the new User model | P1 | 4 | Backend Eng |
| CODE-3 | Add PAN/GST uniqueness constraints + the missing loan-status index | P2 | 1 | Backend Eng |
| CODE-4 | Global auth/loan state (Zustand or Context) with persistence | P1 | 4 | Mobile Eng |
| CODE-5 | Structured logging (pino/winston) with request IDs & PII redaction | P2 | 2 | Backend Eng |
| CODE-6 | Centralize error handling via AppError + handlePrismaError | P2 | 1 | Backend Eng |
| CODE-7 | Pagination + eager loading on list endpoints (kill N+1) | P2 | 2 | Backend Eng |
| CODE-8 | Audit and remove the unused Firebase dependency if OTP is backend-driven | P3 | 2 | Mobile Eng |

### Notes that matter

- schema.prisma keeps both the legacy customers table and the new User model. Pick User, migrate the data, and retire the legacy path before more code depends on the ambiguity (CODE-2).

- The mobile app uses only local useState — no Redux/Zustand/Context. State is lost on navigation (the review’s LoginScreen phone example is real) and every screen refetches on mount. A small global store for auth + loan state fixes both (CODE-4).

- Firebase 12.x is bundled in the mobile app, but authentication is handled by the custom backend OTP flow. If Firebase isn’t actually used, removing it meaningfully cuts bundle size (CODE-8).

# Phase 3 — Testing, DevOps & monitoring (Weeks 3–6)

There are currently zero tests, no Dockerfile, no CI, and no error tracking. This phase makes the system safe to change and safe to operate. Start the test harness as soon as the payment and auth flows stabilize.

| ID | Fix | Pri | Days | Owner |
| --- | --- | --- | --- | --- |
| OPS-1 | Jest + supertest: critical-path tests for auth, loans, payments | P1 | 5 | Backend Eng |
| OPS-2 | Dockerize backend + admin; docker-compose with Postgres | P1 | 2 | DevOps |
| OPS-3 | GitHub Actions CI/CD: lint, typecheck, test, build, deploy to staging | P1 | 2 | DevOps |
| OPS-4 | Error tracking (Sentry) + product analytics (Mixpanel/PostHog) | P1 | 2 | Backend + Mobile |
| OPS-5 | ESLint + Prettier + Husky pre-commit + tsconfig strict | P2 | 1 | Backend Eng |
| OPS-6 | Expo EAS build/OTA + image optimization (expo-image) + lazy tabs | P3 | 3 | Mobile Eng |
| OPS-7 | Redis caching layer (scale prep, optional until needed) | P3 | 2 | Backend Eng |

# Phase 4 — Business & launch gating (parallel, founder-led)

These are not code tasks, but they gate launch harder than any code item. BIZ-1 and BIZ-2 are P0 and must start in Week 1 — they have the longest lead times and everything downstream (real beta, fundraise) depends on them.

| ID | Fix | Pri | Days | Owner |
| --- | --- | --- | --- | --- |
| BIZ-1 | Secure the lending capital partner (NBFC / co-lending); decide the lending model | P0 | 10 | Founder / BD |
| BIZ-2 | Legal & regulatory review: RBI Digital Lending Guidelines, NBFC licensing, DPDP Act | P0 | 10 | Founder / Legal |
| BIZ-3 | Define the explicit revenue model + a unit-economics financial model | P1 | 4 | Founder / Finance |
| BIZ-4 | GTM plan + investor materials (pitch deck, demo video) | P1 | 5 | Founder / Growth |
| BIZ-5 | Closed beta with 50–100 real SMBs, instrumented for the metrics investors ask for | P1 | 8 | Product / Growth |

Effort here is in calendar-days of founder/partner time, not engineering-days — these overlap heavily with the engineering phases.

### The one question to answer this week

Who provides the loan capital — is Svakarma a direct lender, a marketplace, or a distributor? The review flags this as the critical unanswered question, and it cascades into licensing (BIZ-2), the revenue model (BIZ-3), and the underwriting logic engineering builds in INT-6. Decide it before writing the underwriting rules.

# Sequencing & critical path

Weeks are indicative for a team of 2–3 engineers plus founders on the business track. The critical path to a real beta runs: SEC-2 → INT-1 (OTP), INT-2 (CIBIL) → INT-3 (payments) → OPS-1 (tests) → BIZ-5 (beta), with BIZ-1/BIZ-2 running in parallel from day one.

## Week-by-week

| When | Focus |
| --- | --- |
| Week 1 | Engineering: all of Phase 0 (SEC-1–7). Business: start BIZ-1 (capital partner) and BIZ-2 (legal). Select OTP/payment/bureau vendors. |
| Weeks 2–3 | INT-1 (OTP), INT-2 (CIBIL) begin. In parallel: CODE-1/2/3 (schema), CODE-4 (mobile state). OPS-2 (Docker) + OPS-5 (lint) set up. |
| Weeks 3–4 | INT-3 (payments) + INT-4 (storage). OPS-1 (tests) and OPS-3 (CI/CD) come online. CODE-5/6/7 (logging, errors, pagination). |
| Weeks 4–5 | INT-5 (notifications), INT-6 (underwriting), INT-7 (e-sign). OPS-4 (Sentry/analytics). BIZ-3 (financial model). |
| Weeks 5–6 | Hardening, OPS-6/7, end-to-end testing. BIZ-4 (GTM + deck). Prepare BIZ-5 beta cohort. |
| Weeks 6–8+ | Closed beta with real SMBs (BIZ-5); collect approval/default/retention/NPS data for the fundraise. |

## Definition of “production-ready MVP”

- All P0 items closed; no mocked auth, payments, or bureau calls in the production path.

- Critical-path flows (login, apply, approve, repay) covered by automated tests running in CI.

- Errors tracked in Sentry; key funnels instrumented; rate limiting and validation enforced.

- A signed lending-capital arrangement and a documented regulatory position exist.

# Suggested ownership & next step

The review estimates production-readiness at 8–12 weeks with 1–2 added senior engineers; this plan agrees. A workable split: one senior backend engineer owns Phases 0–1 (security + integrations), one full-stack/mobile engineer owns the mobile half of Phase 0 plus Phase 2 (state, quality), and a part-time DevOps owns Phase 3. Founders own Phase 4 from Week 1.

Recommended next step: confirm the lending-capital model (BIZ-1) and kick off the legal review (BIZ-2) this week, while engineering starts Phase 0 — it needs no decisions and no accounts, so there is no reason to wait. When you are ready to start the code work, I can implement Phase 0 directly in the repo, file by file, for review.